## Sheet1
| Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
Sprint Start Date | 2020-03-07 | 2020-03-24 | 2020-04-01 | 2020-04-15
Sprint End Date | 2020-03-14 | 2020-03-31 | 2020-04-14 | 2020-04-30
Working Days | 10 | 5 | 10 | 10
Team Size | 6 | 6 | 6 | 6
Work Hours Per Day | 3 | 3 | 5 | 5
Total Available Hours | 4 | 5 | 6 | 7
Average Daily Available Hours | 24 | 24 | 24 | 24
Average Productivity % | 80 | 80 | 60 | 60
Productive Hours | 22.4 | 28 | 33.6 | 39.2
Average Daily Productive Hours | 3.2 | 4 | 4.8 | 5.6
Sprint Forecast Week 1 - Points |  |  |  |  | Sprint Forecast Week 1 - Stories
Day of Sprint | Target | Actual |  |  | Day of Sprint | Target | Actual
0 | 3 | 3 |  |  | 0 | 4 | 4
1 | 3 | 2 |  |  | 1 | 3 | 3
2 | 2 | 2 |  |  | 2 | 2 | 3
3 | 1 | 2 |  |  | 3 | 2 | 3
4 | 1 | 0 |  |  | 4 | 1 | 2
5 | 0 | 0 |  |  | 5 | 0 | 0
Sprint Forecast Week 2 - Points |  |  |  |  | Sprint Forecast Week 2 - Stories
Day of Sprint | Forecast | Target | Actual |  | Day of Sprint | Forecast | Target | Actual
0 | 0 | 0 | 0 |  | 0 | 3 | 3 | 3
1 | 0 | 0 | 0 |  | 1 | 3 | 2 | 3
2 | 0 | 0 | 0 |  | 2 | 2 | 2 | 3
3 | 0 | 0 | 0 |  | 3 | 2 | 1 | 3
4 | 0 | 0 | 0 |  | 4 | 1 | 1 | 0
5 | 0 | 0 | 0 |  | 5 | 0 | 0 | 0
Sprint Forecast Week 3 - Points |  |  |  |  | Sprint Forecast Week 3 - Stories
Day of Sprint | Forecast | Target | Actual |  | Day of Sprint | Forecast | Target | Actual
0 |  |  |  |  | 0
1 |  |  |  |  | 1
2 |  |  |  |  | 2
3 |  |  |  |  | 3
4 |  |  |  |  | 4
5 |  |  |  |  | 5
6 |  |  |  |  | 6
7 |  |  |  |  | 7
8 |  |  |  |  | 8
9 |  |  |  |  | 9
10 |  |  |  |  | 10
Sprint Forecast Week 4 - Points |  |  |  |  | Sprint Forecast Week 4 - Stories
Day of Sprint | Forecast | Target | Actual |  | Day of Sprint | Forecast | Target | Actual
0 |  |  |  |  | 0
1 |  |  |  |  | 1
2 |  |  |  |  | 2
3 |  |  |  |  | 3
4 |  |  |  |  | 4
5 |  |  |  |  | 5
6 |  |  |  |  | 6
7 |  |  |  |  | 7
8 |  |  |  |  | 8
9 |  |  |  |  | 9
10 |  |  |  |  | 10